## Sheet1
Tasks for All:
Research: Companies that Shawn mentioned, current VR products in market, Google cardboard products, education and education technology
Based on research, propose an idea, why it's unique, and why we'll be able to accomplish it - For Friday meeting with Shawn | Notes from meeting with Shawn are in our Drive Folder
Complete individual task in list below
To complete before Tuesday, 9/20 | Person
Draft and agree on a Development Process you will use this semester | Moises to lead this - review with team on Monday
Set team and personal Goals for the semester | All - Monday meeting
Draw your first system Architecture Diagram, noting important aspects of the scaffolding (open source reuse, dependencies, potential ratholes, development status, core technology) | Charlie - Moises
Create a team and code Repository on Github | Moises
Create a Progress Board to track your weekly development progress | Charlie
Begin your Weekly Progress Log, which includes:
Progress this week
Commit graph
Links to new artifacts
Plan for next week
Key learnings and actions from your weekly retro
Risks
Email a snapshot of your Weekly Progress Log to your Company Champion | Jaya